## Introduction
Introduction: Use of the template
Planning Sheet:
1. In "Planning Sheet" "Colum "K" you must register "No. of Team members"; "Daily working hours" and "No. of days in the Sprint"
Available hours of work (resources) in the Sprint is calculated.
This is used to compare with the total amount of hours you allocates to all the tasks "Planning Sheet" Cell "K1" (=SUM of Column D).
If you over allocates / estimates too many hours of work for the period, you will get a warning in column B - (cell B5)
2. In Column "A" register Story ID / Task ID and describe Products and Tasks in Planning Sheet (Stories / Tasks) in Column "B"
3. Define No. of necessary Resources for each Task in Column "C"
4. Estimate each Task using Three Point Estimation (Value A, B, C) in Column "E"; "F"; "G".
The estimate must be based on how many clock hours is necessary for the work done with the resources given.
The Weighted Average ("M") value in column "H" and Standard Deviation in column "I" will automatically be calculated
If Standard Deviation > 10% of "Weighted Average", it's recommendable to break down the task in two or more and recalculate again
(You will get a warning in column "J")
The "Total amount of work" for each task (Column "D") is calculated automatically by "No. of necessary resources" * "The Weighted average"M"
5. The Values of "Total amount of work" in Column "D" is tranferred to the "Sprint Backlog Burndown" sheet automatically.
Sprint Backlog Burndown
6. Every day at the Daily Sprint meeting The Team register - starting in Column "D" (1. daily reporting) how many working hours there is left at each task.
If there haven't been done anything on a task, there's no registration, of course.
From the column where the registration is done and to the right (from column D to M the values automatically is corrected.
The Burn Down Chart Sheet is updated automatically.
Burn Down Chart
Is a Graphical representation showing:
1. The linear path (the red graph) through the Sprint, based on the assumption that all resources available are fully used daily.
2. Compared to this graph the other graph (the blue graph) show how it actually went based on the Daily Sprint Meeting, where updating the progress
(Effort left) in the Sprint Backlog Burndown Sheet is an essential task.

## Planning Sheet
| Sprint |  |  | Effort "Day 0" calculated using three point estimates (or PERT) | [5 empty] | 56
|  | No. of team member per task | Total amount of work | [5 empty] | No. of Team members: | 4
Story ID | Stories / Tasks |  |  | Read note i cells for calculations |  |  |  |  | Daily working hours: | 5
Task ID | Planned |  |  | Estimate effort in hours |  |  |  |  | No. of Sprint Days: | 5
|  |  |  | A | B | C | M | Sd | Available hours of work (resources): | 100
1 | Repositories og interfaces | 4 | 16 | 3 | 4 | 5 | 4 | 0.4
2 | Metoder | 4 | 20 | 4 | 5 | 6 | 5 | 0.4
3 | JSON-filer | 4 | 7.2 | 1 | 2 | 2 | 1.8 | 0.2 | Deviation (Sd) >10%- Break down and reestimate
4 | On get/on set | 4 | 4.8 | 1 | 1 | 2 | 1.2 | 0.2 | Deviation (Sd) >10%- Break down and reestimate
5 | Design siderne | 4 | 8 | 2 | 2 | 2 | 2 | 0
|  |  | 0 |  |  |  | 0 | 0
|  |  | 0 |  |  |  | 0 | 0
|  |  | 0 |  |  |  | 0 | 0
|  |  | 0 |  |  |  | 0 | 0
|  |  | 0 |  |  |  | 0 | 0
|  |  | 0 |  |  |  | 0 | 0
|  |  | 0 |  |  |  | 0 | 0
|  |  | 0 |  |  |  | 0 | 0
|  |  | 0 |  |  |  | 0 | 0
|  |  | 0 |  |  |  | 0 | 0
|  |  | 0 |  |  |  | 0 | 0
|  |  | 0 |  |  |  | 0 | 0
|  |  | 0 |  |  |  | 0 | 0
|  |  | 0 |  |  |  | 0 | 0
|  |  | 0 |  |  |  | 0 | 0
|  |  | 0 |  |  |  | 0 | 0
|  |  | 0 |  |  |  | 0 | 0
|  |  | 0 |  |  |  | 0 | 0
|  |  | 0 |  |  |  | 0 | 0
|  |  | 0 |  |  |  | 0 | 0
|  |  | 0 |  |  |  | 0 | 0
|  |  | 0 |  |  |  | 0 | 0
|  |  | 0 |  |  |  | 0 | 0
|  |  | 0 |  |  |  | 0 | 0
|  |  | 0 |  |  |  | 0 | 0
|  |  | 0 |  |  |  | 0 | 0
|  |  | 0 |  |  |  | 0 | 0
|  |  | 0 |  |  |  | 0 | 0
|  |  | 0 |  |  |  | 0 | 0
|  |  | 0 |  |  |  | 0 | 0
|  |  | 0 |  |  |  | 0 | 0
|  |  | 0 |  |  |  | 0 | 0
|  |  | 0 |  |  |  | 0 | 0
|  |  | 0 |  |  |  | 0 | 0
|  |  | 0 |  |  |  | 0 | 0
|  |  | 0 |  |  |  | 0 | 0
|  |  | 0 |  |  |  | 0 | 0
|  |  | 0 |  |  |  | 0 | 0
|  |  | 0 |  |  |  | 0 | 0
|  |  | 0 |  |  |  | 0 | 0
Note on D2: Is used in Sprint Backlog Burndown Calculated by "M" * No of team member per task
Note on H5: Weighted average: (A+3*B+C)/5 = M If there are more than 3 team members to calculate efforts, you have to take the average of the middle estimates for value "B". Fx if there are 4 members: (a+3*(B1+B2)/2+C)/5 =M
Note on I5: Standard deviation: (C-A)/5 =Sd
Note on H7: Effort is calulated using "Tree point estimating" (PERT) - The Standard Deviation is only used for calulating if the deviation is higher than 10% If so you will get a warning
Note on A15: Id of the story. To simplify linking to the product backlog
Note on B17: Task description are written in the language that team likes. It does not have to be management understandable or "correct".

## Sprint Backlog Burndown
| Sprint | Effort "Day 0" calculated using three point estimates (or PERT)
Days in sprint / Effort left
Story ID | Stories / Tasks | 0 | 1 | 2 | 3 | 4 | 5 | Linear count down based
Task ID | Planned | 56 | 44.8 | 33.6 | 22.4 | 11.2 | 0 | on the resources available
| Effort left | 56 | 11 | 11 | 11 | 11 | 11 |  | 11.2
1 | Repositories og interfaces | 16 | 0 | 0 | 0 | 0 | 0
2 | Metoder | 20 | 3 | 3 | 3 | 3 | 3
3 | JSON-filer | 7.2 | 0 | 0 | 0 | 0 | 0
4 | On get/on set | 4.8 | 0 | 0 | 0 | 0 | 0
5 | Design siderne | 8 | 8 | 8 | 8 | 8 | 8
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on C7: Values in column D (Day 0) is calculated values from "Planning sheet" using three point estimating